## Sheet1
ENCLOSURE
1. clean enclosure (dust/shit) | 2
2. setup CAM for CNC machine for top cover drills | 15
3. load part into CNC, setup & run | 3
4. setup CAM for CNC machine to ethernet plugs | 15
5. load part into CNC, setup & run | 3
6. clean dust and crap | 2
PCB PREP
0. have all components in inventory. not having them will cause additional hand soldering requirement later on.
1. apply solder paste to PCB | 2
2. place all SMD components on PCB (microcontroller, level shifters, analog switches, resistors, caps, voltage regulator, diodes) | 10
3. setup reflow oven, run PCB through it | 5
4. inspect, fixup unintended bridges | 2
5. solder all connectors/headers onto PCB | 5
6. program microcontroller using pickit | 2
TOP COVER / BOTTOM COVER
1. Solder connector PCB to NGC/NGC/SNES case-mount connectors. Especially NGC is tricky due to small contacts | 15
2. Solder header wires to connector PCB's; according to schematic | 15
3. Fix connector to enclosure, using hot-glue | 5
4. Solder 8-pin and 4-pin headers to LCD module | 3
5. Glue LCD in top cover | 1
6. Drill 3mm power led, aligned left/vertical center to LCD | 1
7. Drill 6.5mm hole in bottom part of enclosure for menu button | 2
8. Push in power led and menu button | 3
9. Solder ground of power led to one side of menu button switch | 1
10. Solder 3-pin header to power led/menu switch | 1
11. Glue down led | 1
CABLES
1. Cut off female end of SNES/N64/NGC connector | 1
2. Strip cable properly | 2
3. Use document to find connector pinout | 2
4. Crimp RJ10/RJ45 properly to stripped wires | 1
FINISH
1. Test everything | 5
2. Glue PCB to bottom part of enclosure | 2
3. Tuck away wires and screw everything shut | 2
total time | 129 | minutes
without setup | 99